## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
05NiRBypu0GTTSh9D3ywKckAOA4a | python flask API for the timeseries prototype | Closing | Completed | Medium | Balasuriya B.L.I.S it21803666 | Balasuriya B.L.I.S it21803666 | 09/05/2025 | 09/05/2025 | 06/12/2025 | false | false | 06/12/2025 | Balasuriya B.L.I.S it21803666
21dGxL91s0yeL50095meA8kAHWrD | Design PCB for smart-plugs. | Executing | In progress | Medium | Siriwardhana S.M.D.S it21813948 | Siriwardhana S.M.D.S it21813948 | 09/22/2025 | 09/22/2025 | 09/29/2025 | false | false
32YfKGpR-EuQ7zzslrjUeckAP438 | Identify the research problem and gap. | Closing | Completed | Medium | Siriwardhana S.M.D.S it21813948 | Siriwardhana S.M.D.S it21813948 | 01/06/2025 | 01/06/2025 | 01/13/2025 | false | false | 01/13/2025 | Siriwardhana S.M.D.S it21813948
3P1KLCx5SEGldXw6ZRWI_ckABjbc | Integrating ML component | Planning | Not started | Medium | Balasuriya B.L.I.S it21803666 | Balasuriya B.L.I.S it21803666 | 09/17/2025 |  | 11/12/2025 | false | false
3rd_7cHNYkSUs2DwgnlHh8kACqib | Predictive Analytics | Monitoring and controlling | In progress | Medium | Pivithuru N.H.A.S it21389160 | Pivithuru N.H.A.S it21389160 | 05/06/2025 | 05/06/2025 | 10/02/2025 | false | false
4_PKYxrbH0O4lAEKxziF8ckAPXSl | Proposal Presentation | Closing | Completed | Medium | Welikalage R.Y.W it21808166;Pivithuru N.H.A.S it21389160;Balasuriya B.L.I.S it21803666;Siriwardhana S.M.D.S it21813948 | Pivithuru N.H.A.S it21389160 | 01/01/2025 | 01/01/2025 | 01/27/2025 | false | false | 01/27/2025 | Pivithuru N.H.A.S it21389160
76gH61ZTxEaiUROoIkYgUMkAGWhl | Update code for Wi‑Fi Provisioning & Device Identity. | Closing | Completed | Medium | Siriwardhana S.M.D.S it21813948 | Siriwardhana S.M.D.S it21813948 | 03/03/2025 | 03/03/2025 | 03/10/2025 | false | false | 03/10/2025 | Siriwardhana S.M.D.S it21813948
8cJnkCkP20mGZC_ikLXr8ckAO3lG | Proposal (Draft) submission | Closing | Completed | Medium | Welikalage R.Y.W it21808166;Pivithuru N.H.A.S it21389160;Balasuriya B.L.I.S it21803666;Siriwardhana S.M.D.S it21813948 | Pivithuru N.H.A.S it21389160 | 15/09/2024 | 15/09/2024 | 12/10/2024 | false | false | 12/10/2024 | Pivithuru N.H.A.S it21389160
8tq-2krb9ESgeKg-LWn9yckAHgwl | Integrate smart-plug with AWS IoT services. | Closing | Completed | Medium | Siriwardhana S.M.D.S it21813948 | Siriwardhana S.M.D.S it21813948 | 03/24/2025 | 03/24/2025 | 03/31/2025 | false | false | 03/31/2025 | Siriwardhana S.M.D.S it21813948
91xsgRDlekWj--q5gactQskABMFv | Setup AWS Data Pipeline & Storage for main-meter IoT device. | Closing | Completed | Medium | Siriwardhana S.M.D.S it21813948 | Siriwardhana S.M.D.S it21813948 | 08/05/2025 | 08/05/2025 | 09/08/2025 | false | false | 09/08/2025 | Siriwardhana S.M.D.S it21813948
9rSFvgtj60G-vLXnY5poF8kAOIa3 | Device Registration & Management | Closing | Completed | Medium | Pivithuru N.H.A.S it21389160 | Pivithuru N.H.A.S it21389160 | 02/01/2025 | 02/01/2025 | 03/15/2025 | false | false | 03/15/2025 | Pivithuru N.H.A.S it21389160
Bcc3Dcx8U0W7Mfa6Lt_waskAEdlf | Energy Consumption Thresholds | Closing | Completed | Medium | Pivithuru N.H.A.S it21389160 | Pivithuru N.H.A.S it21389160 | 02/05/2025 | 02/05/2025 | 04/05/2025 | false | false | 04/05/2025 | Pivithuru N.H.A.S it21389160
C200J2990Emtaybpx1XxIMkAG8kC | Historical Data Analytics | Closing | Completed | Medium | Pivithuru N.H.A.S it21389160 | Pivithuru N.H.A.S it21389160 | 04/15/2025 | 04/15/2025 | 09/01/2025 | false | false | 09/01/2025 | Pivithuru N.H.A.S it21389160
Cv3rj458OESKx93SYtQYN8kAL5ca | Energy-Saving Suggestions | Closing | Completed | Medium | Pivithuru N.H.A.S it21389160 | Pivithuru N.H.A.S it21389160 | 09/05/2025 | 09/05/2025 | 09/10/2025 | false | false | 09/10/2025 | Pivithuru N.H.A.S it21389160
DLsAe-wQrkONjpIn2TPY7skACqZ_ | Write Arduino code for energy monitoring. | Closing | Completed | Medium | Siriwardhana S.M.D.S it21813948 | Siriwardhana S.M.D.S it21813948 | 02/24/2025 | 02/24/2025 | 03/03/2025 | false | false | 03/03/2025 | Siriwardhana S.M.D.S it21813948
ELglnS8ydUKNgQ_Kvbfm1skANHLr | State aware recursive forecasting algorithm | Closing | Completed | Medium | Balasuriya B.L.I.S it21803666 | Balasuriya B.L.I.S it21803666 | 08/02/2025 | 08/02/2025 | 05/14/2025 | false | false | 05/14/2025 | Balasuriya B.L.I.S it21803666
EvH3xJLEJ0WDY5tPUFS8F8kAMhc- | Main Meter Integration | Closing | Completed | Medium | Pivithuru N.H.A.S it21389160 | Pivithuru N.H.A.S it21389160 | 08/15/2025 | 08/15/2025 | 09/10/2025 | false | false | 09/10/2025 | Pivithuru N.H.A.S it21389160
Ewsx1Gf9yEG_c44mvSuPwMkAN8DA | TAF Submission | Closing | Completed | Medium | Welikalage R.Y.W it21808166;Pivithuru N.H.A.S it21389160;Balasuriya B.L.I.S it21803666;Siriwardhana S.M.D.S it21813948 | Pivithuru N.H.A.S it21389160 | 11/15/2024 | 11/15/2024 | 12/08/2024 | false | false | 12/08/2024 | Pivithuru N.H.A.S it21389160
HcbiKMtQcUeH_xOgOvDxgMkAHuJU | Creating Rule Set to generate personalized suggestions | Closing | Completed | Medium | Welikalage R.Y.W it21808166 | Welikalage R.Y.W it21808166 | 05/05/2025 | 05/05/2025 | 08/31/2025 | false | false | 08/31/2025 | Welikalage R.Y.W it21808166
HyQect7510KQp43aEp2q8skALQQf | Proposal (Final) submission | Closing | Completed | Medium | Welikalage R.Y.W it21808166;Pivithuru N.H.A.S it21389160;Balasuriya B.L.I.S it21803666;Siriwardhana S.M.D.S it21813948 | Pivithuru N.H.A.S it21389160 | 01/01/2025 | 01/01/2025 | 01/24/2025 | false | false | 01/24/2025 | Pivithuru N.H.A.S it21389160
ISSPrT08-02Mo0RJwjqTlMkAITQ8 | Study about the hardware components. | Closing | Completed | Medium | Siriwardhana S.M.D.S it21813948 | Siriwardhana S.M.D.S it21813948 | 01/13/2025 | 01/13/2025 | 01/20/2025 | false | false | 01/20/2025 | Siriwardhana S.M.D.S it21813948
Iqt7zoQ3fkylfc3sNO8XZ8kAKLgb | Notifications & Alerts | Planning | Not started | Medium | Pivithuru N.H.A.S it21389160 | Pivithuru N.H.A.S it21389160 | 09/17/2025 |  | 10/01/2025 | false | false
JF0HUMXj0Um6cZNa-4YweMkAER_N | Final Report Draft | Closing | Completed | Medium | Welikalage R.Y.W it21808166;Pivithuru N.H.A.S it21389160;Balasuriya B.L.I.S it21803666;Siriwardhana S.M.D.S it21813948 | Pivithuru N.H.A.S it21389160 | 08/15/2025 | 08/15/2025 | 08/30/2025 | false | false | 08/30/2025 | Pivithuru N.H.A.S it21389160
MXoTCzJgdkuWh1CidQ3n3skAMtUd | Create Final Report Documents | Executing | In progress | Medium | Welikalage R.Y.W it21808166;Pivithuru N.H.A.S it21389160;Balasuriya B.L.I.S it21803666;Siriwardhana S.M.D.S it21813948 | Pivithuru N.H.A.S it21389160 | 08/15/2025 | 08/15/2025 | 09/30/2025 | false | false
NABYYP-E40OEhx0RK87gJMkAPPNS | Real-Time Data Fetching | Closing | Completed | Medium | Pivithuru N.H.A.S it21389160 | Pivithuru N.H.A.S it21389160 | 01/15/2025 | 01/15/2025 | 03/15/2025 | false | false | 03/15/2025 | Pivithuru N.H.A.S it21389160
NNLcBDkUSUy183-IoGPNyckAFIOT | Dashboard & UI Layout | Closing | Completed | Medium | Pivithuru N.H.A.S it21389160 | Pivithuru N.H.A.S it21389160 | 01/05/2025 | 01/05/2025 | 04/05/2025 | false | false | 04/05/2025 | Pivithuru N.H.A.S it21389160
NcU75szTy02rnvzBVY4HbckANaH9 | Real-Time Visualization | Closing | Completed | Medium | Pivithuru N.H.A.S it21389160 | Pivithuru N.H.A.S it21389160 | 01/15/2025 | 01/15/2025 | 04/05/2025 | false | false | 04/05/2025 | Pivithuru N.H.A.S it21389160
PmsuHZ6oskqzlVtYD6CODMkAC9Id | Model Selection by Test Data | Closing | Completed | Medium | Welikalage R.Y.W it21808166 | Welikalage R.Y.W it21808166 | 05/03/2025 | 05/03/2025 | 08/31/2025 | false | false | 08/31/2025 | Welikalage R.Y.W it21808166
Q8ScgHeerkWzfmvnu1bLwMkAF8SJ | Testing & Refinement LLM Model | Closing | Completed | Medium | Welikalage R.Y.W it21808166 | Welikalage R.Y.W it21808166 | 05/06/2025 | 05/06/2025 | 08/01/2025 | false | false | 08/01/2025 | Welikalage R.Y.W it21808166
QViQLjrvtkyM5RzD8a7kG8kAH6RB | Train ML model for energy usage scenario forecasting. | Closing | Completed | Medium | Siriwardhana S.M.D.S it21813948 | Siriwardhana S.M.D.S it21813948 | 05/06/2025 | 05/06/2025 | 06/03/2025 | false | false | 06/03/2025 | Siriwardhana S.M.D.S it21813948
QaenpPoEIECWZgRNrxiAYMkAJnWi | Aggregation of data | Closing | Completed | Medium | Balasuriya B.L.I.S it21803666 | Balasuriya B.L.I.S it21803666 | 07/20/2025 | 07/20/2025 | 02/13/2025 | false | false | 02/13/2025 | Balasuriya B.L.I.S it21803666
S8eAX0Xz6kGc5_RGVf17TMkAEgNt | Fine tuning LLM model more | Planning | Not started | Medium | Welikalage R.Y.W it21808166 | Welikalage R.Y.W it21808166 | 09/17/2025 |  | 10/01/2025 | false | false | 10/01/2025
SISUH3CYRk2BDE3OcrvrQckAI1De | feature engineering | Closing | Completed | Medium | Balasuriya B.L.I.S it21803666 | Balasuriya B.L.I.S it21803666 | 07/20/2025 | 07/20/2025 | 04/17/2025 | false | false | 04/17/2025 | Balasuriya B.L.I.S it21803666
UqXtKp93OUKU51eHRRKGjckAERE4 | PP2 Presentation | Closing | Completed | Medium | Welikalage R.Y.W it21808166;Pivithuru N.H.A.S it21389160;Balasuriya B.L.I.S it21803666;Siriwardhana S.M.D.S it21813948 | Pivithuru N.H.A.S it21389160 | 09/10/2025 | 09/10/2025 | 09/15/2025 | false | false | 09/15/2025 | Pivithuru N.H.A.S it21389160
W6eg08ufEUGrLnjj4rLD2MkADKcR | PP1 Presentation | Closing | Completed | Medium | Welikalage R.Y.W it21808166;Pivithuru N.H.A.S it21389160;Balasuriya B.L.I.S it21803666;Siriwardhana S.M.D.S it21813948 | Pivithuru N.H.A.S it21389160 | 04/01/2025 | 04/01/2025 | 04/07/2025 | false | false | 04/07/2025 | Pivithuru N.H.A.S it21389160
Wu8lrBNzLUmhVUHOUgjXr8kABxoY | Cost Calculation & Billing | Closing | Completed | Medium | Pivithuru N.H.A.S it21389160 | Pivithuru N.H.A.S it21389160 | 08/02/2025 | 08/02/2025 | 08/20/2025 | false | false | 08/20/2025 | Pivithuru N.H.A.S it21389160
X2q4UVveAUC5QAxNAXSw-skACLFC | Model Testing/ Training | Closing | Completed | Medium | Balasuriya B.L.I.S it21803666 | Balasuriya B.L.I.S it21803666 | 07/20/2025 | 07/20/2025 | 04/20/2025 | false | false | 04/20/2025 | Balasuriya B.L.I.S it21803666
Z37Fp8afpkmsX5lUzyAW7skAKNF5 | Data Collection & Preprocessing for training LLM | Closing | Completed | Medium | Welikalage R.Y.W it21808166 | Welikalage R.Y.W it21808166 | 03/20/2025 | 03/20/2025 | 06/30/2025 | false | false | 06/30/2025 | Welikalage R.Y.W it21808166
botGpejq7Eyu8a4_nHYT2skAIHF8 | Model Validation & Fine-Tuning | Closing | Completed | Medium | Welikalage R.Y.W it21808166 | Welikalage R.Y.W it21808166 | 08/05/2025 | 08/05/2025 | 08/10/2025 | false | false | 08/10/2025 | Welikalage R.Y.W it21808166
dAL-1Vt4hUiYykXTaZMkoMkAAMGs | Accessibility & Theme Management | Closing | Completed | Medium | Pivithuru N.H.A.S it21389160 | Pivithuru N.H.A.S it21389160 | 07/01/2025 | 07/01/2025 | 08/01/2025 | false | false | 08/01/2025 | Pivithuru N.H.A.S it21389160
exuXa0JWCEGBlu8ZknGCF8kAO5Wc | Monthly bill summary logic | Executing | In progress | Medium | Balasuriya B.L.I.S it21803666 | Balasuriya B.L.I.S it21803666 | 08/20/2025 | 08/20/2025 | 09/30/2025 | false | false
gD93lrAXMUKIIOSvehgUjckAFyrL | Logbook document | Executing | In progress | Medium | Pivithuru N.H.A.S it21389160 | Pivithuru N.H.A.S it21389160 | 01/05/2025 | 01/05/2025 | 10/31/2025 | false | false
gq3XGuEQX0ClrTXFYDBSjskABpiC | Study about Arduino programming. | Closing | Completed | Medium | Siriwardhana S.M.D.S it21813948 | Siriwardhana S.M.D.S it21813948 | 02/10/2024 | 02/10/2024 | 02/17/2025 | false | false | 02/17/2025 | Siriwardhana S.M.D.S it21813948
iCFaM_VVv0O6TMNYdNPYNskADNgI | Checklist Doc Submission | Closing | Completed | Medium | Welikalage R.Y.W it21808166;Pivithuru N.H.A.S it21389160;Balasuriya B.L.I.S it21803666;Siriwardhana S.M.D.S it21813948 | Pivithuru N.H.A.S it21389160 | 04/06/2025 | 04/06/2025 | 04/07/2025 | false | false | 04/07/2025 | Pivithuru N.H.A.S it21389160
kiZkUAvZHkKzl70qtaAUFMkAKQzp | OCR Integration | Closing | Completed | Important | Welikalage R.Y.W it21808166 | Welikalage R.Y.W it21808166 | 08/15/2025 | 08/15/2025 | 09/01/2025 | false | false | 09/01/2025 | Welikalage R.Y.W it21808166
m5Pyu4zi10WjrH24lixPP8kABVSI | Manufacturing, Enclosure & Compliance. | Planning | Not started | Medium | Siriwardhana S.M.D.S it21813948 | Siriwardhana S.M.D.S it21813948 | 10/06/2025 | 10/06/2025 | 10/20/2025 | false | false
n5YH4cmvv0ugP5ydubXBLMkAEPiO | Project Initialization & Environment | Closing | Completed | Medium | Pivithuru N.H.A.S it21389160 | Pivithuru N.H.A.S it21389160 | 01/01/2025 | 01/01/2025 | 02/01/2025 | false | false | 02/01/2025 | Pivithuru N.H.A.S it21389160
oG5rMHEO_0aD3-m3kfs8_8kAKqUT | Generative AI Integration with main web application | Closing | Completed | Medium | Welikalage R.Y.W it21808166 | Welikalage R.Y.W it21808166 | 09/09/2025 | 09/09/2025 | 08/24/2025 | false | false | 08/24/2025 | Welikalage R.Y.W it21808166
oLlWauWtvUeYYShxNmJzDckAB0c5 | Fine tuning AI model using Runpod | Closing | Completed | Medium | Welikalage R.Y.W it21808166 | Welikalage R.Y.W it21808166 | 09/05/2025 | 09/05/2025 | 08/24/2025 | false | false | 08/24/2025 | Welikalage R.Y.W it21808166
orMYg7mJqUSAYNRxrxmNFMkAMajA | Authentication & User Profiles | Closing | Completed | Medium | Pivithuru N.H.A.S it21389160 | Pivithuru N.H.A.S it21389160 | 01/02/2025 | 01/02/2025 | 03/10/2025 | false | false | 03/10/2025 | Pivithuru N.H.A.S it21389160
phHkKJGM2EWmpE5RcDlDU8kAP6pO | Research paper draft | Closing | Completed | Medium | Welikalage R.Y.W it21808166;Pivithuru N.H.A.S it21389160;Balasuriya B.L.I.S it21803666;Siriwardhana S.M.D.S it21813948 | Pivithuru N.H.A.S it21389160 | 07/01/2025 | 07/01/2025 | 08/01/2025 | false | false | 08/01/2025 | Pivithuru N.H.A.S it21389160
qALkgERAz0KnBqqitj-nSskAJ0CJ | fine-tuning the model | Executing | In progress | Medium | Balasuriya B.L.I.S it21803666 | Balasuriya B.L.I.S it21803666 | 08/20/2025 | 08/20/2025 | 10/01/2025 | false | false
qarSVh8x8ECJhYYyJoDj6MkAIh9V | Charter Submission | Closing | Completed | Medium | Welikalage R.Y.W it21808166;Pivithuru N.H.A.S it21389160;Balasuriya B.L.I.S it21803666;Siriwardhana S.M.D.S it21813948 | Pivithuru N.H.A.S it21389160 | 12/12/2024 | 12/12/2024 | 01/05/2025 | false | false | 01/05/2025 | Pivithuru N.H.A.S it21389160
r2YY-kZzyUGazo6kEehILskAGl5X | Individual report | Planning | Not started | Medium | Balasuriya B.L.I.S it21803666 | Balasuriya B.L.I.S it21803666 | 09/17/2025 |  | 10/15/2025 | false | false
rXZ6Ie2L_0eugNIgDejQRckABgCQ | Create Final Presentation Document | Monitoring and controlling | In progress | Medium | Welikalage R.Y.W it21808166;Pivithuru N.H.A.S it21389160;Balasuriya B.L.I.S it21803666;Siriwardhana S.M.D.S it21813948 | Pivithuru N.H.A.S it21389160 | 09/16/2025 | 09/16/2025 | 10/05/2025 | false | false
s3g5-MzCfUq9HQxsugaHUMkACcw5 | Setup AWS Data Pipeline & Storage for smart-plugs. | Closing | Completed | Medium | Siriwardhana S.M.D.S it21813948 | Siriwardhana S.M.D.S it21813948 | 03/31/2025 | 03/31/2025 | 04/05/2025 | false | false | 04/05/2025 | Siriwardhana S.M.D.S it21813948
sUHkFQzaeUq2SADqGQvNX8kAP_Xe | Develop energy monitoring IoT device for main-meter. | Closing | Completed | Medium | Siriwardhana S.M.D.S it21813948 | Siriwardhana S.M.D.S it21813948 | 07/01/2025 | 07/01/2025 | 07/29/2025 | false | false | 07/29/2025 | Siriwardhana S.M.D.S it21813948
shDVLyqm3kGlT0UM_Hh0VMkADTUQ | Integrate the Threshold & Safety Automation functions. | Closing | Completed | Medium | Siriwardhana S.M.D.S it21813948 | Siriwardhana S.M.D.S it21813948 | 03/10.2025 | 03/10.2025 | 03/17/2025 | false | false | 03/17/2025 | Siriwardhana S.M.D.S it21813948
ueVZWoUDMUaGPMdr9LL5DckAIA5A | data pre-processing for time-series analysis | Closing | Completed | Medium | Balasuriya B.L.I.S it21803666 | Balasuriya B.L.I.S it21803666 | 08/20/2025 | 08/20/2025 | 02/10/2025 | false | false | 02/10/2025 | Balasuriya B.L.I.S it21803666
uujQlf_LV0WezOmldrTUZckADsn_ | Select hardware components and programming language. | Closing | Completed | Medium | Siriwardhana S.M.D.S it21813948 | Siriwardhana S.M.D.S it21813948 | 02/03/2025 | 02/03/2025 | 02/10/2025 | false | false | 02/10/2025 | Siriwardhana S.M.D.S it21813948
v8Tb7nKVpUOCeFykI8uVS8kAMF9w | Testing & Deployment | Executing | In progress | Medium | Pivithuru N.H.A.S it21389160 | Pivithuru N.H.A.S it21389160 | 06/05/2025 | 06/05/2025 | 10/05/2025 | false | false
vjlzz3EXi0uhHxwRH4Xb1MkAN8cv | Calibration and testing the hardware components. | Closing | Completed | Medium | Siriwardhana S.M.D.S it21813948 | Siriwardhana S.M.D.S it21813948 | 03/17/2025 | 03/17/2025 | 03/24/2025 | false | false | 03/24/2025 | Siriwardhana S.M.D.S it21813948
x2Mmu9w-IkeiFweoztWRAskAPVov | Finalize Research Paper | Planning | Not started | Medium | Welikalage R.Y.W it21808166;Pivithuru N.H.A.S it21389160;Balasuriya B.L.I.S it21803666;Siriwardhana S.M.D.S it21813948 | Pivithuru N.H.A.S it21389160 | 09/17/2025 |  | 09/21/2025 | false | false
ykOh-bFO4Emz-7IQXXr2WckAPE7z | Assemble the hardware components. | Closing | Completed | Medium | Siriwardhana S.M.D.S it21813948 | Siriwardhana S.M.D.S it21813948 | 02/17/2025 | 02/17/2025 | 02/24/2025 | false | false | 02/24/2025 | Siriwardhana S.M.D.S it21813948

## Plan name
Plan name | R25 - 065 Planner
Plan ID | MC-hrjsFVEW7A-mqzpDHTMkAHsqh
Date of export | 09/18/2025